## Sheet1
Theater in the Pines Bridge Replacement Cost Summary-Title II Funds Requested
Forest Service Personnel
Title | GS/WG Level | Cost Per Day (8HR day) | # DAYS | Total Costs | Work Duties
Equipment Operator | WG-8 | 252 | 3 | 756 | Construct footing and transport and set new bridges with backhoe | 7188.12
Project Manager | GS-5/5 | 177 | 4 | 708 | Provide supervision and techinical support. Assist with design, transportation, bridge footing, installation and demolition and removal of existing bridges.
Mason | GS-6 | 143.83 | 5 | 719.15 | Repair stone bridge footings after removal of existing bridges, any stone work repairs associated with new bridges. Assist in demolition and removal of existing bridges.
Recreation Seasonal | GS-4 | 113.69 | 5 | 568.45
Recreation Seasonal | GS-3 | 101.21 | 5 | 506.05
Purchasing Agent | GS-7 | 200 | 2 | 400 | Prepare and submit bridge bids for purchase, other project related purchases
Engineering/Design/Heritage
Archaeologist | GS-12 | 328.88 | 1 | 328.88 | Bridge design (2-days total)
Landscape Architect | GS-12 | 388.81 | 1 | 388.81 | Bridge design (2-days total)
Engineer | GS-12 | 376.7 | 5 | 1883.5 | Bridge design (2 weeks total 10 days)
Volunteer Coordination
Volunteer Coordinator | GS-7-4 | 232.32 | 4 | 929.28 | Coordinate volunteer projects and supervise on the ground volunteer work.
Materials/Supplies
| Description |  |  | Estimated Cost | Explanation of Cost Estimate
East Bridge | Custom bridge design. Treated Wood timber stringer (rough) with historical elements. (8'X18') |  |  | 15000 | Based off of bids received 2010 for Glued-laminated slab bridge | 30207
West Bridge | Same |  |  | 15000 | Based off of bids received 2010 for Glued-laminated slab bridge
Both Bridges | Misc. supplies: Sand, lime, cement. |  |  | 207 | Stone-work associated with removal and installation of bridges
Total Title II Funds Requested |  |  |  | 37395.12
Theater in the Pines Bridge Replacement Cost Summary-Forest Service/Volunteer Contributions
Forest Service Personnel
| GS/WG Level | Cost Per Day (8HR day) | # DAYS | Total Costs | Work Duties
Equipment Operator | WG-8 | 252 | 3 | 756 | Construct footing and transport and set new bridges with backhoe | 6788.12
Project Manager | GS-5/5 | 177 | 4 | 708 | Provide supervision and techinical support. Assist with design, transportation, bridge footing, installation and demolition and removal of existing bridges. | 3759.81
Mason | GS-6 | 143.83 | 5 | 719.15 | Repair stone bridge footings after removal of existing bridges, any stone work repairs associated with new bridges. Assist in demolition and removal of existing bridges.
Recreation Seasonal | GS-4 | 113.69 | 5 | 568.45
Recreation Seasonal | GS-3 | 101.21 | 5 | 506.05
Engineering/Design/Heritage
Archaeologist | GS-12 | 328.88 | 1 | 328.88 | Bridge design (2-days total)
Landscape Architect | GS-12 | 388.81 | 1 | 388.81 | Bridge design (2-days total)
Engineer | GS-12 | 376.7 | 5 | 1883.5 | Bridge design (2 weeks total of 10 days)
Volunteer Coordination
Volunteer Coordinator | GS-7-4 | 232.32 | 4 | 929.28 | Coordinate volunteer projects and supervise on the ground volunteer work.
Equipment
| FOR Rate (Lease amount) |  | # Days | Total | Mileage Costs (miles per day x # Days x mileage cost) | 2065.7
FS Truck (1) | 7.07 | per day | 10 | 70.7 | 120
FS Truck (2) | 6.6 | per day | 10 | 66 | 84
FS Dump truck | 8.3 | per day | 10 | 83 | 284
FS Trail Cat/Backhoe | 11.96 | per day | 10 | 119.6 | 1238.4
Total Forest Service Contributions |  |  |  | 8853.82
Volunteer Contributions
| Number of Volunteers | Hourly Value | # Hours | Total Value | Work Duties
Volunteer Labor (18+) | 5 | 15 | 16 | 1200 | Assist in emoval of old bridges, site preparation and finish work, most likely with school groups, eagle scouts, or BYU Alumi Camp.
Volunteer Labor (< 18 ) | 5 | 10 | 16 | 800
Total Volunteer Contributions |  |  |  | 2000